Unit DTL1

Project Initiation Request

Data Services Simplification

Date: 		01/02/2026

Doc. Version: 	1.0

Template version: 1.0

The latest version of this controlled document is stored in Teams under “DataHub Dev. Team”.

This template is based on PM² V3.0

For the latest version of this template please visit the PM² Wiki

| Project Title: |  | Data Services Simplification |  |  |
| --- | --- | --- | --- | --- |
| Initiator: |  | Jan Bliki | Group: | DTL1 |
| Project Owner (PO): |  | Jan Bliki | Solution Provider (SP): | DTL1 HoU |
| Type of Delivery: |  | ☐ In-house ☐ Outsourced ☒ Mix ☐ Not-known | Start Date: | Q1 2026 |
|  |  |  | Target Delivery Date: | Q4 2028 |
| Estimated budget: |  | Core budget estimate: Infrastructure investments: approx. 650k-950k Content & governance investments: approx. 120 days/year + consultant budget (50k-250k) Data lakehouse infrastructure: 250k/year Recurring O&M from 2028: 95k-145k/year Internal effort (PD/FTE): Project manager / data management: 120 days/year Data management: 80 days/year Data Governance: 200 days/year Data transformation: 60-180 days/year (increasing yearly) |  |  |
| Context/ Situation (Business Need/ Problem / Opportunity) |  |  |  |  |
| The current EEA data infrastructure is highly fragmented across multiple systems (SDI, DataHub, Data Explorer, DiscoData, Discomap, DataHub Lab). This results in: - inconsistent metadata quality - siloed storage of spatial & tabular data - low user discoverability - difficulty integrating cross‑thematic environmental datasets - outdated infrastructure not aligned with EU‑level data initiatives - high maintenance costs and slow development cycles - limited readiness for AI‑based data processing User feedback from Eurostat, ETCs, the Commission UX study, and public analysts highlights that users struggle to find datasets, cannot easily integrate geospatial and non‑spatial data, and have inconsistent experiences across platforms. The situation creates operational inefficiencies, increased costs, and lost opportunities for broader public engagement and interoperability. |  |  |  |  |
| EEA’s strategic goal / Legal Basis |  |  |  |  |
| The initiative directly supports: - Mission 2: Enhanced EEA Data Services & Data Management Modernisation - IT Strategy, Data Strategy, and Digital Capability Strategy alignment - EU interoperability and data-sharing frameworks, including: - Green Deal Data Space - INSPIRE - data.europa.eu - GEOSS - Digital Twins - Destination Earth It addresses obligations relating to ensuring accessible, high‑quality environmental data for policymakers, citizens, EU institutions, and international partners. |  |  |  |  |
| Outcomes / Benefits (high level) |  |  |  |  |
| - A unified DataHub platform replacing >6 fragmented systems. - Improved data discoverability through simplified navigation and data‑first presentation. - Metadata consistency using AI‑assisted curation and automated quality checks. - Single data lakehouse architecture enabling cross‑thematic integration. - Integration with external portals to increase visibility and reuse of EEA data. - Reduced operational costs through consolidation and automation. - Greater accessibility to large datasets, including geospatial data. - Higher AI readiness through structured, harmonised datasets and grid‑based frameworks. |  |  |  |  |
| Impact (optional - high level) |  |  |  |  |
| Internal impact: - Streamlined workflows for data custodians. - Reduced reliance on manual metadata work. - Increased automation and lower maintenance overhead. - Stronger cross-unit collaboration enabled via shared tooling. External impact: - Easier access for the public, researchers, and policy makers. - Clearer user experience with consistent exploration tools. - Improved trust in EEA data through transparency and standardisation. - Increased uptake of EEA data in EU and global ecosystems. |  |  |  |  |
| Success Criteria |  |  |  |  |
| - Launch of unified DataHub replacing SDI, DataHub, Data Explorer, DiscoData, Discomap, and DataHub Lab. - ≥80% reduction in manual metadata editing effort. - All priority datasets available in harmonised formats (grid‑based or geospatial units). - Full integration of data lakehouse with common workspace and public dissemination layer. - Demonstrated interoperability with EU Green Deal Data Space and data.europa.eu. - Web analytics showing increased dataset discoverability and reduced bounce rates. |  |  |  |  |
| Assumptions (high level) |  |  |  |  |
| - IT infrastructure (common workspace, lakehouse) is available and expandable. - Data custodians and experts contribute time for metadata harmonisation. - External contractors remain available for UI redesign, metadata upgrades, and system integration. - AI agent framework can be deployed securely inside EEA infrastructure. - Corporate cybersecurity requirements can be met without major redesign. |  |  |  |  |
| Constraints (high level) |  |  |  |  |
| - Need to maintain ongoing operations while systems are merged. - Cybersecurity requirements following the 2024 incident impose strict limitations on public analytics environments. - Budget is spread across multiple years and depends on staged investments. - Legacy systems still serve critical data consumption workflows that cannot be interrupted. - External dependencies (Eurostat, Data Spaces, INSPIRE) introduce mandatory protocol alignment. |  |  |  |  |
| Risks (high level) |  |  |  |  |
| - Technical risk: Integration of SDI + DataHub + lakehouse may reveal unforeseen complexities. - Security risk: AI‑assisted tools must comply with cybersecurity rules and the AI Act. - Resource risk: Limited internal staff and dependency on consultants. - Operational risk: Migration of historical metadata and datasets is labor‑intensive. - Interoperability risk: Misalignment with evolving EU data standards. - Adoption risk: Stakeholders may need significant training to adopt the new workflows. |  |  |  |  |
| EEA risks level: | - The initiative affects all data dissemination systems, all thematic dataflows, and multiple units across the agency. - It impacts public perception, external data partners, and integration with EU‑wide infrastructures. - AI functionality (metadata agents) introduces additional governance obligations under the AI Act. |  |  |  |